## For development MVP Backlog
🚀 MVP BACKLOG — DEEPTECH HOURLY MARKETPLACE
Target: Credibility MVP (Phase-1)
Sprint Size: 2 weeks
EPIC 1 — USER & ACCESS MANAGEMENT
ST-101: User Registration & Login
Story
As a user, I want to register and log in as a Buyer or Expert so I can access the platform.
Acceptance Criteria
Email/password signup
Role selection (Buyer / Expert)
Email verification
Secure login/logout
Out of Scope
Social login
SSO
ST-102: Basic User Profile
Story
As a user, I want a profile so others can understand who I am.
Acceptance Criteria
Name, bio, domain
Location (country)
Profile visibility toggle
🟦 EPIC 2 — EXPERT ONBOARDING & VETTING
ST-201: Expert Profile Creation
Story
As an Expert, I want to create a detailed profile to showcase my deep-tech experience.
Acceptance Criteria
Domain selection
Experience summary
Hourly rate
Availability calendar
ST-202: Expert Vetting Workflow
Story
As an Admin, I want to review and approve experts to ensure platform quality.
Acceptance Criteria
Admin review dashboard
Approve / reject / request info
Vetting status visible on profile
🟦 EPIC 3 — PROBLEM-FIRST PROJECT INTAKE
ST-301: Structured Project Creation
Story
As a Buyer, I want to define my problem clearly so I can get the right expert.
Acceptance Criteria
Domain selection
Problem description
TRL level selection
Risk category (tech / regulatory / scale)
Expected outcome type
ST-302: Project Visibility & Status
Story
As a Buyer, I want to manage my projects in one place.
Acceptance Criteria
Draft / Active / Completed status
Editable before hiring
Archive functionality
🟦 EPIC 4 — EXPERT DISCOVERY & MATCHING
ST-401: Expert Search
Story
As a Buyer, I want to search experts relevant to my problem.
Acceptance Criteria
Search by domain
Filter by availability
Filter by hourly rate
ST-402: Expert Recommendation (Rule-Based)
Story
As a Buyer, I want expert suggestions based on my project intake.
Acceptance Criteria
Rule-based matching
Shows top 3 experts
Explainable recommendations
🟦 EPIC 5 — HOURLY CONTRACTING
ST-501: Hourly Contract Creation
Story
As a Buyer, I want to hire an expert on an hourly basis.
Acceptance Criteria
Hourly rate confirmation
Weekly hour cap
Start & end date
Contract acceptance by expert
ST-502: Hour Logging
Story
As an Expert, I want to log my hours transparently.
Acceptance Criteria
Manual hour entry
Date & time
Description field
Editable before submission
🟦 EPIC 6 — DECISION & VALUE LOGGING
ST-601: Decision Log Attachment
Story
As an Expert, I want to attach insights to each hour logged.
Acceptance Criteria
Mandatory value tag:
Insight gained
Assumption tested
Risk reduced
Decision made
ST-602: Buyer Review of Logged Hours
Story
As a Buyer, I want to review hours before payment.
Acceptance Criteria
Hour-by-hour visibility
Approve / query hours
Comment on entries
🟦 EPIC 7 — PAYMENTS & ESCROW
ST-701: Hourly Escrow Setup
Story
As a Buyer, I want funds held securely while work is ongoing.
Acceptance Criteria
Escrow funded on contract start
Funds locked per week
Visible balance
ST-702: Weekly Invoicing
Story
As a Buyer, I want weekly invoices for approved hours.
Acceptance Criteria
Auto-generated invoices
PDF export
Email notification
🟦 EPIC 8 — LEGAL & IP SAFETY
ST-801: Auto NDA Generation
Story
As a Buyer, I want an NDA automatically applied to protect IP.
Acceptance Criteria
NDA template selection
Auto-sign on contract acceptance
Versioned storage
ST-802: IP Ownership Declaration
Story
As both parties, we want clarity on IP ownership before work starts.
Acceptance Criteria
Buyer owns / Shared / Expert owns options
Mandatory selection
Locked after contract start
🟦 EPIC 9 — COMMUNICATION & WORKSPACE
ST-901: Project Chat
Story
As users, we want a dedicated chat per project.
Acceptance Criteria
Buyer–expert messaging
Timestamped messages
File attachments
ST-902: Project File Repository
Story
As users, we want a place to store project documents.
Acceptance Criteria
Upload / download files
Access control
Activity log
🟦 EPIC 10 — ADMIN & GOVERNANCE
ST-1001: Admin Dashboard
Story
As an Admin, I want visibility into platform activity.
Acceptance Criteria
Active projects
Active contracts
Disputes
ST-1002: Dispute Flagging
Story
As a Buyer or Expert, I want to flag issues.
Acceptance Criteria
Flag contract
Reason selection
Admin notification
🧭 MVP EXIT CRITERIA (CRITICAL)
MVP is DONE when:
✔ Buyer can hire an expert hourly
✔ Expert logs hours with decision/value tags
✔ NDA & IP are enforced
✔ Payment flows end-to-end
✔ 10 real deep-tech engagements complete successfully

## Features Overview
FEATURE LIST — DEEPTECH HOURLY FREELANCE PLATFORM
1. CORE MARKETPLACE (FOUNDATION)
1.1 User & Account Management
Buyer / Expert / Organization accounts
Individual & company profiles
Availability calendar
Hourly rate management (base + context-based)
1.2 Hourly Contracting & Payments
Hourly contracts with caps
Manual + auto time tracking
Weekly invoicing
Hourly escrow
Auto pause / resume
Dispute management workflow
1.3 Marketplace Discovery
Search & filter experts
Domain-based browsing
Availability-aware ranking
Saved searches & alerts
2. DEEPTECH-SPECIFIC DIFFERENTIATORS
2.1 Problem-First Project Intake
Structured project creation:
Domain (AI, Robotics, Climate, Infra, etc.)
TRL level
Risk category (tech, regulatory, scale)
Expected outcome type (decision, validation, design)
2.2 Capability-Based Expert Profiles
Domain expertise mapping
System-level experience indicators
Prior project types (advisory, execution, R&D)
Patents / papers / products (optional verification)
Failure experience (optional, trust-building)
2.3 Context-Sensitive Hourly Pricing
Different hourly rates for:
Advisory
Architecture review
Hands-on execution
Buyer sees why the rate differs
2.4 Expert Verification & Vetting
Manual vetting workflow
Tiered expert levels (General / Advanced / Deep-Tech Verified)
Vetting badges visible on profile
3. IP, CONFIDENTIALITY & GOVERNANCE
3.1 Built-In Legal Framework
Auto NDA generation per project
IP ownership declaration at project start
Jurisdiction selection
Versioned agreement records
3.2 Secure Project Workspace
Project-specific workspace
Restricted file sharing
Activity logs
Exportable audit trail
3.3 IP Contribution Tracking
Hour-to-artifact linkage
Decision & design traceability
Contribution timeline
4. HOURLY VALUE & TRANSPARENCY
4.1 Decision & Insight Logging
Every logged hour tagged with:
Insight gained
Assumption tested
Risk reduced
Decision made
4.2 Value Monitoring
Low-value hour alerts
Scope drift detection
Buyer & expert visibility
4.3 Structured Deliverables
Architecture notes
Validation reports
Risk assessments
Decision summaries
5. MULTI-EXPERT & ENTERPRISE FEATURES
5.1 Expert Pods (Hourly)
Multi-expert hiring per project
Individual hourly billing
Shared workspace
Pod dashboard
5.2 Organization & Portfolio Accounts
Centralized billing
Multi-project management
Expert pools
Usage analytics
5.3 Accelerator / Incubator Mode
Pre-approved expert lists
Startup portfolio tracking
Subsidized / sponsored hours
6. TRUST & REPUTATION (BEYOND RATINGS)
6.1 Advanced Reputation System
Problem types solved
Domains worked across
Peer endorsements
Engagement outcomes
6.2 Dispute Resolution with Reviewers
Neutral technical reviewers
Evidence-based resolution
Outcome-linked refunds
7. AI-ASSISTED (NON-INTRUSIVE)
7.1 AI Matching Assistant
Expert suggestions based on problem intake
Skill gap alerts
Risk area highlighting
7.2 Engagement Health Monitor
Flags stalled projects
Suggests scope reset
Predicts success likelihood
8. GENERAL MARKETPLACE SUPPORT (NON-DEEPTECH)
8.1 Standard Freelance Mode
Skill-based profiles
Hourly gigs
Basic contracts
Faster onboarding
8.2 Tiered Experience
Open marketplace for general work
Gated access for deep-tech projects
9. ADMIN & PLATFORM CONTROLS
9.1 Platform Governance
Expert approval workflows
Project risk scoring
Compliance exports
9.2 Analytics & Reporting
GMV tracking
Hour utilization
Domain demand heatmaps
Expert performance metrics
10. VERIFIABLE MVP FEATURE CUT (START HERE)
Phase-1 MUST-HAVE
Hourly contracts
Problem intake templates
Manual expert vetting
NDA + IP templates
Decision logs
Escrow
Phase-2 SCALE
Capability graph
Multi-expert pods
Reputation system
Secure workspace
Phase-3 MOAT
AI matching
Value monitoring
Enterprise & accelerator mode